## Slide 1: Strategic Planning
30 Levers
  19 Levers FY2014
189 Actions
  108 Actions FY2014

## Slide 2: LEVER LEADERS (19 Levers FY2014)
1.1 Jeff Cawlfield
1.2 Debra Robinson and Nancy Stone
1.3 Jeff Cawlfield and Larry Gragg
2.1 K. Krishnamurthy and Jim Drallmeier
2.2 Kent Wray
2.3 K. Krishnamurthy and Jim Drallmeier
2.4 Andy Careaga
2.5 Henry Wiebe
2.7 Shenethia Manuel
3.1 Kelvin Erickson
3.2 Henry Wiebe and Edna Grover-Bisker
3.3 Phil Whitefield and Ted Ruth
3.4 Laura Stoll and Shenethia Manuel
3.5 Joan Nesbitt and Jim Murphy
3.8 Phil Whitefield
3.9 Joan Nesbitt
4.1 Henry Wiebe
4.2 Kelvin Erickson, Klaus Woelk
4.5 Venkata Allada

## Slide 3: Theme 1 – Develop and Inspire Creative Thinkers and Leaders and Life-long Success
Lever 1.1: Require all undergraduate students to participate in some significant experiential activity before graduation
Action 1.1.1: Create a defining comprehensive list of activities that are supported by research as significant experiential activities. Create a consensus definition of experiential learning
Begin building a comprehensive list of activities that are supported by research as significant experiential activities (Target: completion by December 2013)

## Slide 4: Theme 1 – Develop and Inspire Creative Thinkers and Leaders and Life-long Success
Action 1.1.2 : Incorporate experiential/service learning into the core curriculum in all degree programs at any level beginning in the freshmen year [Target: Faculty Senate approval of each curriculum by completion of second year of strategic plan (complete by June 2015)]

## Slide 5: Work Completed to date and future work remaining:
Research by UGS office: how do comparator institutions and TRU’s define “experiential learning”?
First draft definition of “significant experiential learning activity” developed and presented to Provost’s direct reports at the Academic Affairs retreat in August. Circulated to Student Affairs for input.
Second draft is being circulated to faculty for input by department chairs. Input requested by October 31.

## Slide 6: Work Completed to date and future work remaining (continued):
Final consensus definition and guidelines to be submitted to Provost by mid-November. Faculty in each degree program will develop/regulate their own comprehensive list of activities that will count as “significant experiential learning” within the spirit of the definition and guidelines approved by the Provost.
Office of Undergraduate Studies will work with degree programs to develop mechanisms for tracking and assessing completion by each student as part of Degree Audit.

## Slide 7: Best-in-Class Strategic Areas for Investment Committee Members
Purpose: To develop a process to solicit and prioritize input/proposals to recommend four best-in-class strategic areas for investment as noted in the S&T strategic plan Lever 2.1.
Two strategic areas to be chose in January, 2014
Two strategic areas to be chosen in April, 2014
Committee will be dissolved near the end of the 2014 spring semester when it completes its work
Committee members:
 | Name | Constituency | Department
1 | Jim Drallmeier, co-chair | Department Chair | MAE
2 | K. Krishnamurthy, co-chair | VPR | Missouri S&T
3 | Larry Gragg | Department Chair | History & Political Science
4 | Dan Waddill | Department Chair | Physics
5 | Joel Burken | Center Director | CArE
6 | Matt O’Keefe | Center Director | MSE
7 | Daryl Beetner | Faculty | ECE
8 | Beth Cudney | Faculty | EMSE
9 | Robert Landers | Faculty | MAE
10 | Curt Elmore | Faculty | GSE
11 | Yinfa Ma | Faculty | Chemistry
12 | Melanie Mormile | Faculty | Biological Sciences
13 | V. Samaranayake | Faculty | Math & Stat
14 | Joseph Smith | Center Director | CBE
15 | Sajal Das | Department Chair | CSc
16 | Samuel Frimpong | Department Chair | NME
17 | Bih-Ru Lea | Faculty | BIT
18 | Kate Drowne | Faculty | English and Technical Communication
19 | Nancy Stone | Department Chair | Psychological Science
20 | Irina Ivliyeva | Faculty | ALP
21 | Michael Davis | Faculty | Economics

## Slide 8: Strategic Planning
Draft Performance Measures for Departments and Non-degree Awarding Units were submitted September 30, 2013
Departments and Academic Affair Units were requested to update their strategic plans to appropriately reflect the 4 themes and 30 levers that constitute the S&T plan and make an effort to provide 2020 targets. They will report on these plans on January 7, 2014 and January 15, 2014 respectively.
The request for Lever 2.2 and Faculty Hires has been distributed and instructions provided for preparing proposals for 16 faculty positions and are to be submitted to the Provost’s Office on or before October 18, 2013
The review committee will evaluate the proposals and submit its recommendations to the Chancellor and Provost by October 28, 2013. Decisions regarding faculty position awards will be announced November 8, 2013.

## Slide 9: Strategic Planning
Lever 2.5 Modify our conventional methods of teaching to accommodate current, new and advanced technology that will enhance student learning and increase faculty productivity.
Received strategic initiative funding to accomplish redesign of the calculus sequence
Received $132,000 from System with $66,000 match
Two years per course to complete redesign:
Calculus I: Fall 2013 – Spring 2015
Calculus II: Fall 2014 – Spring 2016
Calculus III: Fall 2015 – Spring 2017
Using NCAT and other generally accepted re-design principles as guidelines.

## Slide 10: Strategic Planning
Guidelines for Awarding Strategic Initiative Funding for Lever 3.3 which consists of $500,000 in strategic funding provided by UM System to be matched with $500,000 from external donations was distributed October 2, 2013. Draft Guidelines were attached.
Depending on the number of applications received and approved, it is anticipated a range of 5 to 10 projects will be funded through this program. Applications will be available in the fall semesters of 2013 at a date TBA.
Applications will be reviewed by a university committee consisting of:
Kent Wray
Jeff Cawlfield
Henry Wiebe
Joan Nesbitt
Ted Ruth
Greg Smith
Funding recommendations will be made by the committee to the Chancellor.
Final approval will be made by the Chancellor.